## RTM
Business_Need_ID | FR_ID | User_Story_ID | Test_Case_ID | Priority | Implementation_Status | Test_Status | Evidence_Path | Notes
| FR-001 | US-001 | TC-CAP-001 | Must | Not Started | Not Run |  | Proposed test ID — pending reconciliation
| FR-002 | US-002 | TC-VAL-001 | Must | Not Started | Not Run |  | Proposed test ID — pending reconciliation
| FR-003 | US-003 | TC-VAL-002 | Must | Not Started | Not Run |  | Proposed test ID — pending reconciliation
| FR-004 | US-004 | TC-EXC-001 | Must | Not Started | Not Run |  | Proposed test ID — pending reconciliation
| FR-005 | US-005 | TC-AMD-001 | Must | Not Started | Not Run |  | Proposed test ID — pending reconciliation
| FR-006 | US-006 | TC-AMD-002 | Must | Not Started | Not Run |  | Proposed test ID — pending reconciliation
| FR-007 | US-007 | TC-AMD-003 | Must | Not Started | Not Run |  | Proposed test ID — pending reconciliation
| FR-008 | US-008 | TC-RPT-001 | Must | Not Started | Not Run |  | Proposed test ID — pending reconciliation
| FR-009 | US-009 | TC-BI-001 | Must | Not Started | Not Run |  | Proposed test ID — pending reconciliation
| FR-010 | US-010 | TC-AI-001 | Must | Not Started | Not Run |  | Proposed test ID — pending reconciliation

## User_Stories
Story_ID | Story_Title | FR_ID | Priority | Story_Points | Release | Status | Acceptance_Criteria_Status | Evidence_Path
US-001 | Capture OTC Trade | FR-001 | Must | 3 | R1 | Not Started | Not Verified
US-002 | Automated Trade Validation | FR-002 | Must | 5 | R1 | Not Started | Not Verified
US-003 | Detect Notional Mismatch | FR-003 | Must | 5 | R1 | Not Started | Not Verified
US-004 | Manage Trade Exceptions | FR-004 | Must | 5 | R2 | Not Started | Not Verified
US-005 | Human Approval for Corrections | FR-005 | Must | 5 | R2 | Not Started | Not Verified
US-006 | Preserve Trade Version History | FR-006 | Must | 5 | R2 | Not Started | Not Verified
US-007 | Revalidate Amended Trades | FR-007 | Must | 3 | R2 | Not Started | Not Verified
US-008 | Simulated Regulatory Reporting | FR-008 | Must | 5 | R3 | Not Started | Not Verified
US-009 | Operational Analytics Dashboard | FR-009 | Must | 5 | R3 | Not Started | Not Verified
US-010 | Predictive Risk & AI Investigation | FR-010 | Must | 8 | R4 | Not Started | Not Verified

## RAID_Register
RAID_ID | Type | Description | Impact | Probability | Mitigation_or_Action | Owner | Status
RSK-001 | Risk | Azure or Snowflake access becomes unavailable | High | Low | Verify access; maintain documented local fallback | Project Owner | Open
RSK-002 | Risk | Duplicate processing creates inconsistent trade versions | High | Medium | Implement idempotency and replay tests | Data Engineer | Open
RSK-003 | Risk | Synthetic ML data produces misleading performance | High | Medium | Separate UAT and ML data; test for leakage | ML Engineer | Open
RSK-004 | Risk | LLM provides unsupported trade explanations | High | Medium | Require citations and evidence-grounded responses | AI Engineer | Open
RSK-005 | Risk | Implementation exceeds available time | Medium | Medium | Prioritise Must stories and deliver incrementally | Project Owner | Open
ASM-001 | Assumption | Synthetic fixtures suitable for UAT | Medium | N/A | Validate fixtures against data dictionary | Data Engineer | Pending Validation
ASM-002 | Assumption | Confirmation records can be matched deterministically | High | N/A | Test confirmation matching keys | Data Engineer | Pending Validation
ASM-003 | Assumption | A supported warehouse route is available | High | N/A | Verify Snowflake permissions and compute | Project Owner | Pending Validation
ASM-004 | Assumption | Power BI can connect to reporting data | Medium | N/A | Test Power BI connectivity | BI Developer | Pending Validation
ASM-005 | Assumption | Adequate separate ML training data can be generated | High | N/A | Define and validate ML training dataset | ML Engineer | Pending Validation
ISS-001 | Issue | Cloud permissions, compute and budget not yet verified | High | N/A | Check service permissions, quotas and costs | Project Owner | Open
ISS-002 | Issue | Logical schema not reconciled with Phase 1 dictionary | High | N/A | Complete field-level schema reconciliation | Data Engineer | Open
ISS-003 | Issue | ML training data and labelling approach not finalised | Medium | N/A | Finalise ML dataset and label design | ML Engineer | Open
DEP-001 | Dependency | Phase 1 data dictionary and fixture contracts | High | N/A | Validate Phase 1 data dictionary and source fixtures | Data Engineer | Open
DEP-002 | Dependency | Confirmed implementation environment | High | N/A | Verify Azure and Snowflake permissions, compute and connectivity | Project Owner | In Progress
DEP-003 | Dependency | Stable trade/version identifiers | High | N/A | Finalise trade IDs, version keys and schema constraints | Data Engineer | Open
DEP-004 | Dependency | Independent confirmation matching rules | High | N/A | Define and test independent confirmation matching rules | Data Engineer | Open
DEP-005 | Dependency | Human approval and authorisation design | High | N/A | Implement approval workflow and role-based permissions | Project Owner | Open
DEP-006 | Dependency | Curated warehouse and dbt models | High | N/A | Build and validate Snowflake tables and dbt models | Data Engineer | Open
DEP-007 | Dependency | Separate model-development data | High | N/A | Prepare separate ML training data and validate data quality | ML Engineer | Open
DEP-008 | Dependency | Model artifacts and serving environment | Medium | N/A | Train model, register artifacts and configure prediction API | ML Engineer | Open
DEP-009 | Dependency | Authorised AI retrieval and knowledge sources | Medium | N/A | Configure authorised retrieval and evidence-grounded AI responses | AI Engineer | Open
DEP-010 | Dependency | Integrated test environment | High | N/A | Prepare integrated environment and end-to-end test cases | Project Owner | Open

## Release_Tracker
Release_ID | Release_Name | Scope | Dependencies | Status | Exit_Criteria | Evidence_Path
R1 | Data Foundation | Trade ingestion, validation and independent confirmation checks | DEP-001, DEP-002, DEP-003, DEP-004 | Not Started | Ingestion and validation tests pass; T-1001 mismatch detected
R2 | Trade Controls | Exception management, approvals, amendments, versioning and revalidation | R1, DEP-005 | Not Started | Approval, versioning and revalidation tests pass
R3 | Reporting & Analytics | Simulated reporting, dbt reporting marts and Power BI dashboards | R2, DEP-006 | Not Started | Simulated reporting works; dashboard KPIs reconcile with SQL
R4 | Predictive Intelligence | ML training, MLflow, FastAPI and AI assistant | R1, R2, DEP-007, DEP-008, DEP-009 | Not Started | Model evaluated; API tested; AI answers cite evidence
R5 | Integration & UAT | End-to-end testing, security, performance and traceability verification | R1, R2, R3, R4, DEP-010 | Not Started | End-to-end UAT, security and NFR tests pass; RTM complete